## Sheet2
Internship schedule
Class I | Class II | Class III | Owner | 1st Week |  | 2nd Week |  | 3rd Week |  | 4th Week |  | 5th Week
|  |  |  | A | B | A | B | A | B | A | B | A | B
Task: Tutorial2 development on Jasmine platform | Set-up | 개발환경 구축 | 상필
| Design | Conceptural design | 상필
|  | Implementation design | ALL
| Implementation | ftl_read protocol API 구현 | 규화
|  | address mapping table 구현 | 경환
|  | ftl_write protocol API 구현 | 기환
|  | mapping caching 구현 | 경환
|  | POR 구현 | 규화, 경환
|  | Garbage collection 구현 | 규화
| Testing & Debugging | 1차 구현 검증 | 기환
|  | 2차 구현 검증 | 기환
|  | 최종 테스트 | 기환
| Evaluatation | evaluation between tutorial1 and tutorial2 w/o mapping caching | 기환,경환
|  | evaluation between tutorial1 and tutorial2 w/ mapping caching | 기환,경환
|  | final evaluation | ALL
misc.